## Summary
Section | Items | Labour £ | Materials £ | Total £
01 · Preliminaries & site set-up | 7 | 8196 | 4279.99 | 12475.99
02 · Demolition & enabling works | 7 | 1314.45 | 1000.94 | 2315.39
03 · Foundations, ground-floor slab & drainage | 25 | 13841.91 | 26649.44 | 40491.35
04 · Structure, external walls & roof | 20 | 6343.9 | 18712.84 | 25056.74
05 · Windows, doors & roof lantern | 6 | 2252.4 | 10843.98 | 13096.38
06 · Plastering, screed & floor finishes | 7 | 3857.32 | 5065.34 | 8922.65
07 · Heating & plumbing | 11 | 4837.34 | 7406.18 | 12243.52
08 · Electrical installation | 7 | 6955.8 | 2410.25 | 9366.05
09 · Decoration to the new work | 3 | 1740.03 | 362.55 | 2102.58
10 · Work to the existing house & external make-good | 3 | 366.28 | 1211.65 | 1577.93
11 · Testing, commissioning & handover | 3 | 560.16 | 87.3 | 647.46
TOTAL (client, excl. VAT) | 99 | 50265.6 | 78030.44 | 128296.04
£/m² sanity check (client, excl. VAT)
Scope | Area (m²) | Client £ | £/m² | Industry mid

## Client-Facing
Item | Element | Basic quantity sense-check | Final Client Total (£)
01 · Preliminaries & site set-up
1 | Site supervision & coordination | Day-to-day site supervision and project coordination across the build (about 13 weeks), keeping the trades sequenced and the works on programme. | 3900
2 | Welfare, temporary power & access | Running the site for the duration of the works (about 13 weeks) — a portaloo, a lockable welfare/tool-store unit, a temporary power connection, and a mobile access tower for working at height. | 7535.59
3 | Waste management & disposal | Skip hire, collection and disposal of construction waste throughout the project. | 1040.4
02 · Demolition & enabling works
4 | Asbestos survey allowance | An allowance for an asbestos survey and the safe removal of any minor material found. | 600.09
5 | Form the new rear opening | Demolishing part of the existing rear wall to form the new opening between the house and the rear extension (approx. 7.6 m2), with temporary support to the structure while the opening is formed. | 379.69
6 | Strip out the existing kitchen | Stripping out the existing kitchen units, worktops and appliances to clear the area for the new works. | 664.2
7 | Remove & set aside existing roof tiles | Carefully removing existing roof tiles (approx. 7.0 m2) for reuse where the new roof meets the existing house. | 69.81
8 | Temporary weather protection | Temporary weather protection to the works during construction (approx. 27 m2). | 353.65
9 | Clear vegetation & strip topsoil | Clearing site vegetation and stripping topsoil across the footprint of the new works (approx. 33 m2). | 247.96
03 · Foundations, ground-floor slab & drainage
10 | Excavation & spoil disposal | Excavating the trench foundations and reduced-level dig (approx. 17 m3 in total), including mini-digger hire, setting-out and datum, concrete compaction, and disposal of the excavated spoil, with trench shoring / earthwork support to the 1.5 m deep runs. | 11261.79
11 | Trench-fill foundations & reinforcement | Mass-concrete strip footings (approx. 9.4 m3) with reinforcement, concrete pump hire and lean-mix cavity fill below damp-proof course. | 13828.25
12 | Foundation blockwork & damp-proof course | Foundation blockwork up to damp-proof course (approx. 15.7 m2), including the mortar and a new damp-proof course. | 9743.76
13 | Ground-floor slab & build-up | The new ground-floor slab and build-up over approx. 27 m2 — hardcore sub-base, sand blinding, damp-proof membrane, floor insulation, reinforcement mesh and the concrete slab, including pump hire. | 3834.56
14 | Below-ground drainage | New below-ground drainage connections (approx. 6 m run) with two gullies and the associated fittings, connections and outlets. | 1822.99
04 · Structure, external walls & roof
15 | Steel beam, padstones & lintels | A structural steel beam over the new rear opening, seated on two padstones, plus lintels over the smaller openings (6 nr). | 3148.26
16 | External cavity walls | New insulated cavity walls to approx. 31 m2 per leaf — inner blockwork leaf, full-fill cavity insulation, outer brick leaf, wall ties and cavity closers. | 7605.9
17 | Make good & match existing render | Preparing and re-rendering approx. 11 m2 of existing wall where the new work meets the house — hacking off loose render and repairing defects, applying reinforcement mesh, base coat, primer and finish, and colour-matching to the existing render with a snagging allowance. | 3768.62
18 | Internal stud partition | A new timber stud partition within the extension (approx. 11 m2). | 526.42
19 | Warm flat roof | The new warm flat roof (approx. 35 m2 deck) — 18 mm OSB decking, firring strips to form the drainage falls, roof insulation and a single-ply membrane covering (approx. 39 m2 including laps). | 6189.76
20 | Roof edge, fascias & rainwater goods | Soffits and fascias, edge trims and flashings, and guttering, downpipes and outlets to the new roof edge (approx. 17 m). | 3817.79
05 · Windows, doors & roof lantern
21 | Bi-fold & porch entrance doors | A four-leaf bi-fold door set (approx. 2.3 m) opening the family room to the rear garden, and a pair of glazed entrance doors (approx. 1.5 m) to the new porch - both supplied, fitted, sealed and adjusted. | 4700.81
22 | Windows, boards & cills | Four new windows, supplied and fitted, with window boards and cills to all four openings. | 4194.79
23 | Internal doors | Four new internal doors to the new spaces, supplied and hung. | 950.38
24 | Roof lantern | A prefabricated roof lantern to the rear extension, supplied and installed. | 3250.4
06 · Plastering, screed & floor finishes
25 | Plastering — walls & ceilings | Plasterboard and skim to the new internal walls (approx. 40 m2) and ceilings (approx. 35 m2), to a plastered finish ready for decoration. | 3512.62
26 | Floor screed | A floor screed to the new ground floor (approx. 35 m2). | 909.13
27 | Floor tiling & engineered-wood flooring | Ceramic floor tiling (approx. 11 m2) and engineered-wood flooring (approx. 14 m2) to the new floor areas. | 3438.78
28 | Skirtings & architraves | Second-fix joinery to the new spaces — skirtings (approx. 34 m) and architraves (approx. 20 m). | 1062.12
07 · Heating & plumbing
29 | Boiler & radiator heating | A boiler and a radiator heating system with pipework (5 radiators) serving the new spaces. | 3913.54
30 | Water supply & waste | Extending the mains water supply (approx. 36 m) and new soil and waste pipework (approx. 26 m). | 1546.3
31 | Sinks, WC & utility fittings | A kitchen sink and taps, a utility sink, a WC suite and basin to the cloakroom/WC, and utility-room cabinets and worktops, supplied and fitted. | 4532.48
32 | Extract ventilation & extractor hood | A new extract ventilation unit to the extension, plus a kitchen extractor hood and ducting. | 1400.8
33 | Appliance installation | Installation of the client's kitchen appliances (connection and setting only; the appliances themselves are supplied by others). | 850.4
08 · Electrical installation
34 | Consumer unit & first fix | A consumer-unit upgrade and first-fix wiring — lighting circuits (16 points), socket circuits (20 points) and kitchen appliance circuits (4 points). | 3252.22
35 | Second fix — switches, sockets & fittings | Second-fix electrics — switches and sockets (40 points) and light fittings (16 points). | 5063.04
36 | Testing, certification & making good | Electrical testing and certification, and making good after the services are installed. | 1050.8
09 · Decoration to the new work
37 | Prime & undercoat new woodwork | Priming and undercoating all new woodwork (approx. 34 m). | 623.65
38 | Emulsion to new walls & ceilings | Mist coat and finish coats of emulsion to the new plastered walls and ceilings (approx. 86 m2). | 1071.47
39 | Gloss to external woodwork | A gloss finish to external woodwork (approx. 34 m). | 407.46
10 · Work to the existing house & external make-good
40 | Make good existing walls | Making good the existing walls after the new opening is formed (approx. 18 m2). | 544.96
41 | Tie the new roof into the existing house | Tying the new extension roof into the existing house roof (approx. 6.4 m). | 372.96
42 | External paving & drainage make-good allowance | An allowance for making good and reinstating external paving and drainage disturbed by the works. | 660
11 · Testing, commissioning & handover
43 | Commissioning & testing | Pressure-testing the plumbing and commissioning and balancing the heating, so the services are signed off before handover. | 350.4
44 | Final clean & handover | A final clean of the new works (approx. 35 m2) prior to client handover. | 297.06
| Total client tender sum (excl. VAT) |  | 128296.04

## Builder BoQ
Section | Nr | Description | Unit | Qty | Labour £/unit | Materials £/unit | Labour £ | Materials £ | Line Total £ | Margin £ | Client Total £
01 · Preliminaries & site set-up
01 · Preliminaries & site set-up | 1 | Site supervision and project coordination | week | 13 | 250 | 0 | 3250 | 0 | 3250 | 650 | 3900
01 · Preliminaries & site set-up | 2 | Portaloo hire for duration of project | week | 13 | 12.85 | 72.73 | 167 | 945.49 | 1112.49 | 127.95 | 1240.44
01 · Preliminaries & site set-up | 3 | Temporary site power connection | item | 1 | 167 | 227.27 | 167 | 227.27 | 394.27 | 56.13 | 450.4
01 · Preliminaries & site set-up | 4 | Tool storage and welfare unit hire | week | 13 | 12.85 | 45.45 | 167 | 590.85 | 757.85 | 92.49 | 850.34
01 · Preliminaries & site set-up | 5 | Provide mobile access tower (up to 6m) | item | 1 | 208 | 181.82 | 208 | 181.82 | 389.82 | 59.78 | 449.6
01 · Preliminaries & site set-up | 6 | Mobile access tower hire | week | 13 | 208 | 90.91 | 2704 | 1181.83 | 3885.83 | 658.98 | 4544.81
01 · Preliminaries & site set-up | 7 | Skip hire and waste disposal throughout project | item | 2 | 83.5 | 381.82 | 167 | 763.64 | 930.64 | 109.76 | 1040.4
|  | 01 · Preliminaries & site set-up subtotal |  |  |  |  | 6830 | 3890.9 | 10720.9 | 1755.09 | 12475.99
02 · Demolition & enabling works
02 · Demolition & enabling works | 8 | Asbestos survey and removal (if required) | item | 1 | 83.4 | 454.55 | 83.4 | 454.55 | 537.95 | 62.13 | 600.09
02 · Demolition & enabling works | 9 | Demolish existing rear wall and create opening | m2 | 7.9737 | 8.32 | 0 | 66.34 | 0 | 66.34 | 13.27 | 79.61
02 · Demolition & enabling works | 10 | Temporary support to existing structure during opening works | item | 1 | 83.4 | 181.82 | 83.4 | 181.82 | 265.22 | 34.86 | 300.08
02 · Demolition & enabling works | 11 | Strip out existing kitchen units, worktops and appliances | nr | 1 | 416 | 150 | 416 | 150 | 566 | 98.2 | 664.2
02 · Demolition & enabling works | 12 | Carefully remove existing roof tiles for reuse | m2 | 6.992 | 8.32 | 0 | 58.17 | 0 | 58.17 | 11.63 | 69.81
02 · Demolition & enabling works | 13 | Temporary weather protection during construction | m2 | 27.16 | 6.68 | 4.55 | 181.43 | 123.58 | 305.01 | 48.64 | 353.65
02 · Demolition & enabling works | 14 | Clear site vegetation and topsoil strip | m2 | 32.592 | 6.34 | 0 | 206.63 | 0 | 206.63 | 41.33 | 247.96
|  | 02 · Demolition & enabling works subtotal |  |  |  |  | 1095.38 | 909.95 | 2005.32 | 310.07 | 2315.39
03 · Foundations, ground-floor slab & drainage
03 · Foundations, ground-floor slab & drainage | 15 | Excavate trench foundations | m3 | 34.128 | 31.7 | 0 | 1081.86 | 0 | 1081.86 | 216.37 | 1298.23
03 · Foundations, ground-floor slab & drainage | 16 | Excavate for reduced level dig | m3 | 7.6797 | 31.7 | 0 | 243.45 | 0 | 243.45 | 48.69 | 292.14
03 · Foundations, ground-floor slab & drainage | 17 | Excavated spoil disposal (1.2x bulking factor) | m3 | 43.3436 | 31.7 | 9.09 | 1373.99 | 393.99 | 1767.99 | 314.2 | 2082.19
03 · Foundations, ground-floor slab & drainage | 18 | Mini digger hire for excavation | day | 5 | 0 | 227.27 | 0 | 1136.35 | 1136.35 | 113.64 | 1249.99
03 · Foundations, ground-floor slab & drainage | 19 | Skip hire for spoil removal | qty | 8 | 0 | 318.18 | 0 | 2545.44 | 2545.44 | 254.54 | 2799.98
03 · Foundations, ground-floor slab & drainage | 20 | Set out, profile boards and datum establishment | item | 1 | 167 | 90.91 | 167 | 90.91 | 257.91 | 42.49 | 300.4
03 · Foundations, ground-floor slab & drainage | 21 | Concrete vibrating/compaction | m3 | 28.44 | 63.4 | 0 | 1803.1 | 0 | 1803.1 | 360.62 | 2163.72
03 · Foundations, ground-floor slab & drainage | 22 | Earthwork support / trench shoring | m | 31.6 | 15.85 | 13.64 | 500.86 | 431.02 | 931.88 | 143.27 | 1075.16
03 · Foundations, ground-floor slab & drainage | 23 | Concrete foundation strip footings | m3 | 34.128 | 63.4 | 136.36 | 2163.72 | 4653.69 | 6817.41 | 898.11 | 7715.52
03 · Foundations, ground-floor slab & drainage | 24 | Reinforcement to foundations | t | 4.977 | 208.5 | 727.27 | 1037.7 | 3619.62 | 4657.33 | 569.5 | 5226.83
03 · Foundations, ground-floor slab & drainage | 25 | Concrete pump hire — foundations | item | 1 | 0 | 318.18 | 0 | 318.18 | 318.18 | 31.82 | 350
03 · Foundations, ground-floor slab & drainage | 26 | Lean mix cavity fill below DPC | m2 | 23.7 | 6.34 | 13.64 | 150.26 | 323.27 | 473.53 | 62.38 | 535.9
03 · Foundations, ground-floor slab & drainage | 27 | Foundation blockwork to DPC level | m2 | 56.88 | 14.6 | 130.78 | 830.45 | 7438.77 | 8269.21 | 909.97 | 9179.18
03 · Foundations, ground-floor slab & drainage | 28 | Install damp proof course | m2 | 12.64 | 5.57 | 7.27 | 70.36 | 91.89 | 162.26 | 23.26 | 185.52
03 · Foundations, ground-floor slab & drainage | 29 | Mortar for foundation blockwork | m2 | 47.4 | 0 | 7.27 | 0 | 344.6 | 344.6 | 34.46 | 379.06
03 · Foundations, ground-floor slab & drainage | 30 | Hardcore sub-base and blinding | m3 | 3.8398 | 31.7 | 59.09 | 121.72 | 226.9 | 348.62 | 47.03 | 395.65
03 · Foundations, ground-floor slab & drainage | 31 | Blinding sand layer over hardcore | m2 | 27.16 | 6.34 | 2.73 | 172.19 | 74.15 | 246.34 | 41.85 | 288.19
03 · Foundations, ground-floor slab & drainage | 32 | Damp proof membrane (DPM) | m2 | 27.16 | 6.34 | 1.82 | 172.19 | 49.43 | 221.63 | 39.38 | 261.01
03 · Foundations, ground-floor slab & drainage | 33 | Install insulation to ground floor | m2 | 27.16 | 6.93 | 22.73 | 188.31 | 617.35 | 805.66 | 99.4 | 905.05
03 · Foundations, ground-floor slab & drainage | 34 | Pour concrete floor slab | m3 | 4.4158 | 63.4 | 136.36 | 279.96 | 602.14 | 882.11 | 116.21 | 998.31
03 · Foundations, ground-floor slab & drainage | 35 | Concrete pump hire — floor slab | item | 1 | 0 | 318.18 | 0 | 318.18 | 318.18 | 31.82 | 350
03 · Foundations, ground-floor slab & drainage | 36 | Reinforcement mesh to floor slab | m2 | 27.16 | 15.35 | 4.55 | 417 | 123.58 | 540.58 | 95.76 | 636.34
03 · Foundations, ground-floor slab & drainage | 37 | Below ground drainage connections | m | 6 | 21.13 | 22.73 | 126.8 | 136.38 | 263.18 | 39 | 302.18
03 · Foundations, ground-floor slab & drainage | 38 | Gullies | qty | 2 | 158.5 | 72.73 | 317 | 145.46 | 462.46 | 77.95 | 540.41
03 · Foundations, ground-floor slab & drainage | 39 | Drainage fittings, connections and outlets | nr | 3 | 105.67 | 181.82 | 317 | 545.46 | 862.46 | 117.95 | 980.41
|  | 03 · Foundations, ground-floor slab & drainage subtotal |  |  |  |  | 11534.93 | 24226.76 | 35761.69 | 4729.66 | 40491.35
04 · Structure, external walls & roof
04 · Structure, external walls & roof | 40 | Install steel beam over new opening | t | 0.8761 | 278.91 | 1923.79 | 244.36 | 1685.46 | 1929.82 | 217.42 | 2147.24
04 · Structure, external walls & roof | 41 | Install padstones for steel beam support | qty | 2 | 125 | 36.36 | 250 | 72.72 | 322.72 | 57.27 | 379.99
04 · Structure, external walls & roof | 42 | Install lintels over openings | nr | 6 | 2.92 | 90.91 | 17.52 | 545.46 | 562.98 | 58.05 | 621.03
04 · Structure, external walls & roof | 43 | Construct cavity wall - inner leaf blockwork | m2 | 30.5138 | 14.6 | 34.55 | 445.5 | 1054.25 | 1499.75 | 194.53 | 1694.28
04 · Structure, external walls & roof | 44 | Install cavity wall insulation | m2 | 30.5138 | 6.93 | 20 | 211.56 | 610.28 | 821.84 | 103.34 | 925.18
04 · Structure, external walls & roof | 45 | Construct cavity wall - outer leaf brickwork | m2 | 30.5138 | 29.2 | 104.55 | 891 | 3190.22 | 4081.22 | 497.22 | 4578.44
04 · Structure, external walls & roof | 46 | Install wall ties and cavity closers | qty | 77 | 3.79 | 0.68 | 292 | 52.36 | 344.36 | 63.64 | 408
04 · Structure, external walls & roof | 47 | External render finish | m2 | 10.8 | 13.32 | 40.91 | 143.86 | 441.83 | 585.68 | 72.95 | 658.64
04 · Structure, external walls & roof | 48 | Prepare substrate — hack off loose render and repair defects | m2 | 10.8 | 13.32 | 73.64 | 143.86 | 795.31 | 939.17 | 108.3 | 1047.47
04 · Structure, external walls & roof | 49 | Apply reinforcement mesh, base coat and primer | m2 | 10.8 | 13.32 | 72.73 | 143.86 | 785.48 | 929.34 | 107.32 | 1036.66
04 · Structure, external walls & roof | 50 | Colour-match and snagging allowance to existing render | m2 | 10.8 | 13.32 | 71.82 | 143.86 | 775.66 | 919.51 | 106.34 | 1025.85
04 · Structure, external walls & roof | 51 | Construct timber stud partitions | m2 | 11.2 | 10 | 31.82 | 112 | 356.38 | 468.38 | 58.04 | 526.42
04 · Structure, external walls & roof | 52 | Install roof decking (18mm OSB) | m2 | 34.533 | 10 | 18.18 | 345.33 | 627.81 | 973.14 | 131.85 | 1104.99
04 · Structure, external walls & roof | 53 | Install firring strips for drainage falls | m2 | 34.533 | 10 | 12.73 | 345.33 | 439.61 | 784.94 | 113.03 | 897.96
04 · Structure, external walls & roof | 54 | Install roof insulation | m2 | 34.533 | 6.93 | 29.09 | 239.43 | 1004.56 | 1243.99 | 148.34 | 1392.34
04 · Structure, external walls & roof | 55 | Apply single-ply membrane roof covering | m2 | 39.3676 | 13.32 | 50 | 524.38 | 1968.38 | 2492.76 | 301.71 | 2794.47
04 · Structure, external walls & roof | 56 | Supply and install soffits and fascias | m | 17.46 | 11.1 | 45.45 | 193.81 | 793.56 | 987.36 | 118.12 | 1105.48
04 · Structure, external walls & roof | 57 | Install roof edge trims and flashings | m | 17.46 | 11.1 | 59.09 | 193.81 | 1031.71 | 1225.52 | 141.93 | 1367.45
04 · Structure, external walls & roof | 58 | Install guttering and downpipes | m | 17.46 | 11.1 | 29.09 | 193.81 | 507.91 | 701.72 | 89.55 | 791.27
04 · Structure, external walls & roof | 59 | Install rainwater downpipes, outlets and gutter fittings | nr | 2 | 105.67 | 136.36 | 211.33 | 272.72 | 484.05 | 69.54 | 553.59
|  | 04 · Structure, external walls & roof subtotal |  |  |  |  | 5286.58 | 17011.67 | 22298.26 | 2758.48 | 25056.74
05 · Windows, doors & roof lantern
05 · Windows, doors & roof lantern | 60 | Supply and install bi-fold doors (small, ≤2.4m) | qty | 1 | 292 | 2272.73 | 292 | 2272.73 | 2564.73 | 285.67 | 2850.4
05 · Windows, doors & roof lantern | 61 | Supply and install French doors | qty | 1 | 292 | 1363.64 | 292 | 1363.64 | 1655.64 | 194.76 | 1850.4
05 · Windows, doors & roof lantern | 62 | Supply and install windows | qty | 5 | 58.4 | 608 | 292 | 3040 | 3332 | 362.4 | 3694.4
05 · Windows, doors & roof lantern | 63 | Install window boards/cills | qty | 5 | 58.4 | 27.27 | 292 | 136.35 | 428.35 | 72.03 | 500.38
05 · Windows, doors & roof lantern | 64 | Supply and install internal doors | qty | 4 | 73 | 136.36 | 292 | 545.44 | 837.44 | 112.94 | 950.38
05 · Windows, doors & roof lantern | 65 | Supply and install prefabricated roof lantern | qty | 1 | 417 | 2500 | 417 | 2500 | 2917 | 333.4 | 3250.4
|  | 05 · Windows, doors & roof lantern subtotal |  |  |  |  | 1877 | 9858.16 | 11735.16 | 1361.22 | 13096.38
06 · Plastering, screed & floor finishes
06 · Plastering, screed & floor finishes | 66 | Plasterboard and skim internal walls | m2 | 39.3 | 13.32 | 18.18 | 523.48 | 714.47 | 1237.95 | 176.14 | 1414.09
06 · Plastering, screed & floor finishes | 67 | Plasterboard and skim ceilings | m2 | 35 | 33.3 | 18.18 | 1165.5 | 636.3 | 1801.8 | 296.73 | 2098.53
06 · Plastering, screed & floor finishes | 68 | Install floor screed | m2 | 34.96 | 8.33 | 14.55 | 291.33 | 508.67 | 800 | 109.13 | 909.13
06 · Plastering, screed & floor finishes | 69 | Install ceramic floor tiles | m2 | 11.4 | 44.92 | 43.64 | 512.12 | 497.5 | 1009.62 | 152.17 | 1161.79
06 · Plastering, screed & floor finishes | 70 | Install engineered wood flooring | m2 | 13.8 | 10 | 139.09 | 138 | 1919.44 | 2057.44 | 219.54 | 2276.99
06 · Plastering, screed & floor finishes | 71 | Supply and fix skirtings | m | 33.5 | 8.72 | 6.82 | 292 | 228.47 | 520.47 | 81.25 | 601.72
06 · Plastering, screed & floor finishes | 72 | Supply and fix architraves | m | 20 | 14.6 | 5 | 292 | 100 | 392 | 68.4 | 460.4
|  | 06 · Plastering, screed & floor finishes subtotal |  |  |  |  | 3214.43 | 4604.85 | 7819.28 | 1103.37 | 8922.65
07 · Heating & plumbing
07 · Heating & plumbing | 73 | Install boiler (if new heating system required) | qty | 1 | 292 | 1090.91 | 292 | 1090.91 | 1382.91 | 167.49 | 1550.4
07 · Heating & plumbing | 74 | Install radiators and heating pipework | qty | 5 | 154.85 | 260.73 | 774.25 | 1303.67 | 2077.92 | 285.22 | 2363.14
07 · Heating & plumbing | 75 | Extend mains water supply | m | 36 | 9.73 | 10.91 | 350.4 | 392.76 | 743.16 | 109.36 | 852.52
07 · Heating & plumbing | 76 | Install soil and waste pipework | m | 26 | 9.73 | 13.64 | 253.07 | 354.64 | 607.71 | 86.08 | 693.78
07 · Heating & plumbing | 77 | Supply and install kitchen sink and taps | qty | 1 | 333 | 227.27 | 333 | 227.27 | 560.27 | 89.33 | 649.6
07 · Heating & plumbing | 78 | Supply and install utility sink (if applicable) | qty | 1 | 333 | 136.36 | 333 | 136.36 | 469.36 | 80.24 | 549.6
07 · Heating & plumbing | 79 | Supply and install WC suite and basin to wet rooms | set | 1 | 365 | 436.36 | 365 | 436.36 | 801.36 | 116.64 | 918
07 · Heating & plumbing | 80 | Supply and install utility room cabinets and worktops | nr | 3.5 | 58.4 | 563.64 | 204.4 | 1972.74 | 2177.14 | 238.15 | 2415.29
07 · Heating & plumbing | 81 | Supply and install extract ventilation unit | nr | 1 | 417 | 181.82 | 417 | 181.82 | 598.82 | 101.58 | 700.4
07 · Heating & plumbing | 82 | Install kitchen extractor hood and ducting | qty | 1 | 292 | 318.18 | 292 | 318.18 | 610.18 | 90.22 | 700.4
07 · Heating & plumbing | 83 | Install kitchen appliances | qty | 1 | 417 | 318.18 | 417 | 318.18 | 735.18 | 115.22 | 850.4
|  | 07 · Heating & plumbing subtotal |  |  |  |  | 4031.12 | 6732.89 | 10764.01 | 1479.51 | 12243.52
08 · Electrical installation
08 · Electrical installation | 84 | Upgrade consumer unit (if required) | qty | 1 | 417 | 363.64 | 417 | 363.64 | 780.64 | 119.76 | 900.4
08 · Electrical installation | 85 | First fix wiring - lighting circuits | point | 16 | 52.12 | 2.27 | 834 | 36.32 | 870.32 | 170.43 | 1040.75
08 · Electrical installation | 86 | First fix wiring - socket circuits | point | 20 | 52.12 | 2.73 | 1042.5 | 54.6 | 1097.1 | 213.96 | 1311.06
08 · Electrical installation | 87 | Second fix electrics - switches and sockets | point | 40 | 52.12 | 13.64 | 2085 | 545.6 | 2630.6 | 471.56 | 3102.16
08 · Electrical installation | 88 | Second fix electrics - light fittings | point | 16 | 52.12 | 54.55 | 834 | 872.8 | 1706.8 | 254.08 | 1960.88
08 · Electrical installation | 89 | Electrical testing and certification | item | 1 | 417 | 227.27 | 417 | 227.27 | 644.27 | 106.13 | 750.4
08 · Electrical installation | 90 | Make good after services installation | item | 1 | 167 | 90.91 | 167 | 90.91 | 257.91 | 42.49 | 300.4
|  | 08 · Electrical installation subtotal |  |  |  |  | 5796.5 | 2191.14 | 7987.64 | 1378.41 | 9366.05
09 · Decoration to the new work
09 · Decoration to the new work | 91 | Prime and undercoat all new woodwork | m | 53.5 | 7.63 | 2.27 | 408.38 | 121.45 | 529.83 | 93.82 | 623.65
09 · Decoration to the new work | 92 | Emulsion to walls and ceilings (mist coat + finish coats) | m2 | 85.8 | 9.16 | 1.36 | 785.93 | 116.69 | 902.62 | 168.85 | 1071.47
09 · Decoration to the new work | 93 | Gloss finish to external woodwork | m | 33.5 | 7.63 | 2.73 | 255.72 | 91.45 | 347.17 | 60.29 | 407.46
|  | 09 · Decoration to the new work subtotal |  |  |  |  | 1450.03 | 329.59 | 1779.62 | 322.96 | 2102.58
10 · Work to the existing house & external make-good
10 · Work to the existing house & external make-good | 94 | Make good existing walls after opening creation | m2 | 17.5862 | 13.32 | 13.64 | 234.25 | 239.88 | 474.13 | 70.84 | 544.96
10 · Work to the existing house & external make-good | 95 | Tie new roof into existing house roof | m | 6.395 | 11.1 | 40.91 | 70.98 | 261.62 | 332.6 | 40.36 | 372.96
10 · Work to the existing house & external make-good | 96 | External paving/drainage make-good and reinstatement allowance | item | 1 | 0 | 600 | 0 | 600 | 600 | 60 | 660
|  | 10 · Work to the existing house & external make-good subtotal |  |  |  |  | 305.23 | 1101.5 | 1406.73 | 171.2 | 1577.93
11 · Testing, commissioning & handover
11 · Testing, commissioning & handover | 97 | Plumbing system pressure testing | item | 1 | 146 | 0 | 146 | 0 | 146 | 29.2 | 175.2
11 · Testing, commissioning & handover | 98 | Heating system commissioning and balancing | item | 1 | 146 | 0 | 146 | 0 | 146 | 29.2 | 175.2
11 · Testing, commissioning & handover | 99 | Final clean prior to client handover | m2 | 34.96 | 5 | 2.27 | 174.8 | 79.36 | 254.16 | 42.9 | 297.06
|  | 11 · Testing, commissioning & handover subtotal |  |  |  |  | 466.8 | 79.36 | 546.16 | 101.3 | 647.46
|  | TOTAL (builder → margin → client, excl. VAT) |  |  |  |  | 41888 | 70936.77 | 112824.76 | 15471.28 | 128296.04

## Provisional Estimates
Element | sense-check | Base Client Cost | Developer Risk/DD | Final Client Total | Client check note | Source Task IDs

## Source Mapping
Task ID | Scope | NRM2 | Section | Category | Description | Qty | Unit | Client Total (£)
RE099 | ground_floor_extension | 11.2 | 01 · Preliminaries & site set-up | Waste Management | Skip hire and waste disposal throughout project | 2 | item | 1040.4
RE100 | ground_floor_extension | 11.3 | 01 · Preliminaries & site set-up | Project Management | Site supervision and project coordination | 13 | week | 3900
RE101a | ground_floor_extension | 1.1 | 01 · Preliminaries & site set-up | Site Setup | Portaloo hire for duration of project | 13 | week | 1240.44
RE101b | ground_floor_extension | 1.1 | 01 · Preliminaries & site set-up | Site Setup | Temporary site power connection | 1 | item | 450.4
RE101d | ground_floor_extension | 1.1 | 01 · Preliminaries & site set-up | Site Setup | Tool storage and welfare unit hire | 13 | week | 850.34
RE103 | ground_floor_extension | 1.7 | 01 · Preliminaries & site set-up | Access Scaffolding | Provide mobile access tower (up to 6m) | 1 | item | 449.6
RE104 | ground_floor_extension | 1.7 | 01 · Preliminaries & site set-up | Access Scaffolding | Mobile access tower hire | 13 | week | 4544.81
RE001 | ground_floor_extension | 1.1 | 02 · Demolition & enabling works | Toxic/Hazardous/Contaminated Material Treatment | Asbestos survey and removal (if required) | 1 | item | 600.09
RE002 | ground_floor_extension | 1.2 | 02 · Demolition & enabling works | Major Demolitions and Alterations | Demolish existing rear wall and create opening | 7.9737 | m2 | 79.61
RE003b | ground_floor_extension | 1.2 | 02 · Demolition & enabling works | Major Demolitions and Alterations | Strip out existing kitchen units, worktops and appliances | 1 | nr | 664.2
RE004 | ground_floor_extension | 1.2 | 02 · Demolition & enabling works | Major Demolitions and Alterations | Carefully remove existing roof tiles for reuse | 6.992 | m2 | 69.81
RE006 | ground_floor_extension | 1.3 | 02 · Demolition & enabling works | Temporary Support to Existing Structures | Temporary support to existing structure during opening works | 1 | item | 300.08
RE007 | ground_floor_extension | 1.4 | 02 · Demolition & enabling works | Temporary Diversion Works | Temporary weather protection during construction | 27.16 | m2 | 353.65
RE008 | ground_floor_extension | 1.5 | 02 · Demolition & enabling works | Site Preparation | Clear site vegetation and topsoil strip | 32.592 | m2 | 247.96
RE010 | ground_floor_extension | 2.1 | 03 · Foundations, ground-floor slab & drainage | Groundworks | Excavate trench foundations | 34.128 | m3 | 1298.23
RE010b | ground_floor_extension | 2.1 | 03 · Foundations, ground-floor slab & drainage | Groundworks | Excavated spoil disposal (1.2x bulking factor) | 43.3436 | m3 | 2082.19
RE010c | ground_floor_extension | 2.1 | 03 · Foundations, ground-floor slab & drainage | Groundworks | Mini digger hire for excavation | 5 | day | 1249.99
RE010d | ground_floor_extension | 2.1 | 03 · Foundations, ground-floor slab & drainage | Groundworks | Skip hire for spoil removal | 8 | qty | 2799.98
RE010e | ground_floor_extension | 2.1 | 03 · Foundations, ground-floor slab & drainage | Groundworks | Earthwork support / trench shoring | 31.6 | m | 1075.16
RE010f | ground_floor_extension | 2.1 | 03 · Foundations, ground-floor slab & drainage | Groundworks | Set out, profile boards and datum establishment | 1 | item | 300.4
RE011 | ground_floor_extension | 2.1 | 03 · Foundations, ground-floor slab & drainage | Groundworks | Excavate for reduced level dig | 7.6797 | m3 | 292.14
RE012 | ground_floor_extension | 2.2 | 03 · Foundations, ground-floor slab & drainage | Foundations | Concrete foundation strip footings | 34.128 | m3 | 7715.52
RE012b | ground_floor_extension | 2.2 | 03 · Foundations, ground-floor slab & drainage | Foundations | Concrete pump hire — foundations | 1 | item | 350
RE012c | ground_floor_extension | 2.2 | 03 · Foundations, ground-floor slab & drainage | Foundations | Concrete vibrating/compaction | 28.44 | m3 | 2163.72
RE013 | ground_floor_extension | 2.2 | 03 · Foundations, ground-floor slab & drainage | Foundations | Reinforcement to foundations | 4.977 | t | 5226.83
RE014 | ground_floor_extension | 2.3 | 03 · Foundations, ground-floor slab & drainage | Foundation Walls | Foundation blockwork to DPC level | 56.88 | m2 | 9179.18
RE014b | ground_floor_extension | 2.3 | 03 · Foundations, ground-floor slab & drainage | Foundation Walls | Mortar for foundation blockwork | 47.4 | m2 | 379.06
RE014c | ground_floor_extension | 2.3 | 03 · Foundations, ground-floor slab & drainage | Foundation Walls | Lean mix cavity fill below DPC | 23.7 | m2 | 535.9
RE015 | ground_floor_extension | 2.4 | 03 · Foundations, ground-floor slab & drainage | Basement Excavation and Structures | Install damp proof course | 12.64 | m2 | 185.52
RE016 | ground_floor_extension | 2.5 | 03 · Foundations, ground-floor slab & drainage | Ground Floor Construction | Hardcore sub-base and blinding | 3.8398 | m3 | 395.65
RE016b | ground_floor_extension | 2.5 | 03 · Foundations, ground-floor slab & drainage | Ground Floor Construction | Blinding sand layer over hardcore | 27.16 | m2 | 288.19
RE016c | ground_floor_extension | 2.5 | 03 · Foundations, ground-floor slab & drainage | Ground Floor Construction | Damp proof membrane (DPM) | 27.16 | m2 | 261.01
RE017 | ground_floor_extension | 2.5 | 03 · Foundations, ground-floor slab & drainage | Ground Floor Construction | Install insulation to ground floor | 27.16 | m2 | 905.05
RE018 | ground_floor_extension | 2.5 | 03 · Foundations, ground-floor slab & drainage | Ground Floor Construction | Pour concrete floor slab | 4.4158 | m3 | 998.31
RE018b | ground_floor_extension | 2.5 | 03 · Foundations, ground-floor slab & drainage | Ground Floor Construction | Concrete pump hire — floor slab | 1 | item | 350
RE018c | ground_floor_extension | 2.5 | 03 · Foundations, ground-floor slab & drainage | Ground Floor Construction | Reinforcement mesh to floor slab | 27.16 | m2 | 636.34
RE019 | ground_floor_extension | 2.6 | 03 · Foundations, ground-floor slab & drainage | Drainage | Below ground drainage connections | 6 | m | 302.18
RE019d | ground_floor_extension | 2.6 | 03 · Foundations, ground-floor slab & drainage | Drainage | Gullies | 2 | qty | 540.41
RE019e | ground_floor_extension | 2.6 | 03 · Foundations, ground-floor slab & drainage | Drainage | Drainage fittings, connections and outlets | 3 | nr | 980.41
RE020 | ground_floor_extension | 3.1 | 04 · Structure, external walls & roof | Frame | Install steel beam over new opening | 0.8761 | t | 2147.24
RE021 | ground_floor_extension | 3.1 | 04 · Structure, external walls & roof | Frame | Install padstones for steel beam support | 2 | qty | 379.99
RE023 | ground_floor_extension | 3.3 | 04 · Structure, external walls & roof | Roof | Install roof decking (18mm OSB) | 34.533 | m2 | 1104.99
RE024 | ground_floor_extension | 3.3 | 04 · Structure, external walls & roof | Roof | Install firring strips for drainage falls | 34.533 | m2 | 897.96
RE025 | ground_floor_extension | 3.3 | 04 · Structure, external walls & roof | Roof | Install roof insulation | 34.533 | m2 | 1392.34
RE026 | ground_floor_extension | 3.3 | 04 · Structure, external walls & roof | Roof | Apply single-ply membrane roof covering | 39.3676 | m2 | 2794.47
RE026d | ground_floor_extension | 3.3 | 04 · Structure, external walls & roof | Roof | Supply and install soffits and fascias | 17.46 | m | 1105.48
RE027 | ground_floor_extension | 3.3 | 04 · Structure, external walls & roof | Roof | Install roof edge trims and flashings | 17.46 | m | 1367.45
RE028 | ground_floor_extension | 3.3 | 04 · Structure, external walls & roof | Roof | Install guttering and downpipes | 17.46 | m | 791.27
RE028b | ground_floor_extension | 3.3 | 04 · Structure, external walls & roof | Roof | Install rainwater downpipes, outlets and gutter fittings | 2 | nr | 553.59
RE029 | ground_floor_extension | 3.5 | 04 · Structure, external walls & roof | External Walls | Construct cavity wall - inner leaf blockwork | 30.5138 | m2 | 1694.28
RE030 | ground_floor_extension | 3.5 | 04 · Structure, external walls & roof | External Walls | Install cavity wall insulation | 30.5138 | m2 | 925.18
RE031 | ground_floor_extension | 3.5 | 04 · Structure, external walls & roof | External Walls | Construct cavity wall - outer leaf brickwork | 30.5138 | m2 | 4578.44
RE031b | ground_floor_extension | 2.5 | 04 · Structure, external walls & roof | External Walls | External render finish | 10.8 | m2 | 658.64
RE031c | ground_floor_extension | 2.5 | 04 · Structure, external walls & roof | External Walls | Prepare substrate — hack off loose render and repair defects | 10.8 | m2 | 1047.47
RE031d | ground_floor_extension | 2.5 | 04 · Structure, external walls & roof | External Walls | Apply reinforcement mesh, base coat and primer | 10.8 | m2 | 1036.66
RE031e | ground_floor_extension | 2.5 | 04 · Structure, external walls & roof | External Walls | Colour-match and snagging allowance to existing render | 10.8 | m2 | 1025.85
RE032 | ground_floor_extension | 3.5 | 04 · Structure, external walls & roof | External Walls | Install wall ties and cavity closers | 77 | qty | 408
RE033 | ground_floor_extension | 3.5 | 04 · Structure, external walls & roof | External Walls | Install lintels over openings | 6 | nr | 621.03
RE038 | ground_floor_extension | 3.7 | 04 · Structure, external walls & roof | Internal Walls and Partitions | Construct timber stud partitions | 11.2 | m2 | 526.42
RE034_S | ground_floor_extension | 3.6 | 05 · Windows, doors & roof lantern | Windows and External Doors | Supply and install bi-fold doors (small, ≤2.4m) | 1 | qty | 2850.4
RE034b | ground_floor_extension | 3.6 | 05 · Windows, doors & roof lantern | Windows and External Doors | Supply and install French doors | 1 | qty | 1850.4
RE035 | ground_floor_extension | 3.6 | 05 · Windows, doors & roof lantern | Windows and External Doors | Supply and install windows | 5 | qty | 3694.4
RE039 | ground_floor_extension | 3.8 | 05 · Windows, doors & roof lantern | Internal Doors | Supply and install internal doors | 4 | qty | 950.38
RE071 | ground_floor_extension | 6.1 | 05 · Windows, doors & roof lantern | Prefabricated Buildings and Building Units | Supply and install prefabricated roof lantern | 1 | qty | 3250.4
RE094 | ground_floor_extension | 3.9 | 05 · Windows, doors & roof lantern | Joinery Second Fix | Install window boards/cills | 5 | qty | 500.38
RE040 | ground_floor_extension | 4.1 | 06 · Plastering, screed & floor finishes | Wall Finishes | Plasterboard and skim internal walls | 39.3 | m2 | 1414.09
RE043 | ground_floor_extension | 4.2 | 06 · Plastering, screed & floor finishes | Floor Finishes | Install floor screed | 34.96 | m2 | 909.13
RE044 | ground_floor_extension | 4.2 | 06 · Plastering, screed & floor finishes | Floor Finishes | Install ceramic floor tiles | 11.4 | m2 | 1161.79
RE045 | ground_floor_extension | 4.2 | 06 · Plastering, screed & floor finishes | Floor Finishes | Install engineered wood flooring | 13.8 | m2 | 2276.99
RE046 | ground_floor_extension | 4.3 | 06 · Plastering, screed & floor finishes | Ceiling Finishes | Plasterboard and skim ceilings | 35 | m2 | 2098.53
RE092 | ground_floor_extension | 3.9 | 06 · Plastering, screed & floor finishes | Joinery Second Fix | Supply and fix skirtings | 33.5 | m | 601.72
RE093 | ground_floor_extension | 3.9 | 06 · Plastering, screed & floor finishes | Joinery Second Fix | Supply and fix architraves | 20 | m | 460.4
RE048 | ground_floor_extension | 5.1 | 07 · Heating & plumbing | Sanitary Appliances | Supply and install kitchen sink and taps | 1 | qty | 649.6
RE049 | ground_floor_extension | 5.1 | 07 · Heating & plumbing | Sanitary Appliances | Supply and install utility sink (if applicable) | 1 | qty | 549.6
RE049b | ground_floor_extension | 5.14 | 07 · Heating & plumbing | Fittings and Equipment | Supply and install utility room cabinets and worktops | 3.5 | nr | 2415.29
RE050 | ground_floor_extension | 5.2 | 07 · Heating & plumbing | Services Equipment | Install boiler (if new heating system required) | 1 | qty | 1550.4
RE051 | ground_floor_extension | 5.3 | 07 · Heating & plumbing | Disposal Installations | Install soil and waste pipework | 26 | m | 693.78
RE053 | ground_floor_extension | 5.4 | 07 · Heating & plumbing | Water Installations | Extend mains water supply | 36 | m | 852.52
RE056 | ground_floor_extension | 5.6 | 07 · Heating & plumbing | Space Heating and Air Conditioning | Install radiators and heating pipework | 5 | qty | 2363.14
RE058 | ground_floor_extension | 5.7 | 07 · Heating & plumbing | Ventilation | Install kitchen extractor hood and ducting | 1 | qty | 700.4
RE058b | ground_floor_extension | 5.1 | 07 · Heating & plumbing | Sanitary Appliances | Supply and install WC suite and basin to wet rooms | 1 | set | 918
RE059b | ground_floor_extension | 5.8 | 07 · Heating & plumbing | Ventilation | Supply and install extract ventilation unit | 1 | nr | 700.4
RE091 | ground_floor_extension | 5.14 | 07 · Heating & plumbing | Fittings and Equipment | Install kitchen appliances | 1 | qty | 850.4
RE060 | ground_floor_extension | 5.8 | 08 · Electrical installation | Electrical Installations | Upgrade consumer unit (if required) | 1 | qty | 900.4
RE061 | ground_floor_extension | 5.8 | 08 · Electrical installation | Electrical Installations | First fix wiring - lighting circuits | 16 | point | 1040.75
RE062 | ground_floor_extension | 5.8 | 08 · Electrical installation | Electrical Installations | First fix wiring - socket circuits | 20 | point | 1311.06
RE064 | ground_floor_extension | 5.8 | 08 · Electrical installation | Electrical Installations | Second fix electrics - switches and sockets | 40 | point | 3102.16
RE065 | ground_floor_extension | 5.8 | 08 · Electrical installation | Electrical Installations | Second fix electrics - light fittings | 16 | point | 1960.88
RE067 | ground_floor_extension | 5.8 | 08 · Electrical installation | Electrical Installations | Electrical testing and certification | 1 | item | 750.4
RE068 | ground_floor_extension | 5.11 | 08 · Electrical installation | Builder's Work in Connection with Services | Make good after services installation | 1 | item | 300.4
RE087 | ground_floor_extension | 9.1 | 09 · Decoration to the new work | Painting and Decorating | Prime and undercoat all new woodwork | 53.5 | m | 623.65
RE088 | ground_floor_extension | 9.1 | 09 · Decoration to the new work | Painting and Decorating | Emulsion to walls and ceilings (mist coat + finish coats) | 85.8 | m2 | 1071.47
RE089 | ground_floor_extension | 9.1 | 09 · Decoration to the new work | Painting and Decorating | Gloss finish to external woodwork | 33.5 | m | 407.46
RE072 | ground_floor_extension | 7.1 | 10 · Work to the existing house & external make-good | Minor Demolition and Alteration Work | Make good existing walls after opening creation | 17.5862 | m2 | 544.96
RE073 | ground_floor_extension | 7.1 | 10 · Work to the existing house & external make-good | Minor Demolition and Alteration Work | Tie new roof into existing house roof | 6.395 | m | 372.96
RE078m | ground_floor_extension | 8.3 | 10 · Work to the existing house & external make-good | Paving and Surfacing | External paving/drainage make-good and reinstatement allowance | 1 | item | 660
RE095 | ground_floor_extension | 10.1 | 11 · Testing, commissioning & handover | Testing and Commissioning | Plumbing system pressure testing | 1 | item | 175.2
RE096 | ground_floor_extension | 10.2 | 11 · Testing, commissioning & handover | Testing and Commissioning | Heating system commissioning and balancing | 1 | item | 175.2
RE098 | ground_floor_extension | 11.1 | 11 · Testing, commissioning & handover | Final Cleaning | Final clean prior to client handover | 34.96 | m2 | 297.06

## Notes
Single-storey rear extension, side utility & WC, and entrance porch — Bill of Quantities
Project | Private client, Surrey
Source
Method
Markup | Labour ×1.20, Materials ×1.10